## Team
TEAM MEMBER | ROLE
JASON | SOFTWARE ENGINEER
SARAH | UI/UX DESIGNER
MIKE | DATABASE ADMINISTRATOR

## User Stories
ID | FEATURE | AS A(N) <ACTOR> | I WANT TO BE ABLE TO <DESCRIPTION> | SO THAT I CAN | ESTIMATE (HOURS) | ASSIGNED TO | SPRINT #
1.1 | NEW USER REGISTER FOR AN ACCOUNT ACCESS THE TASK MANAGEMENT APP | NEW USER | REGISTER FOR AN ACCOUNT | ACCESS THE TASK MANAGEMENT APP | 2 | JASON | 1
1.2 | REGISTERED USER LOG INTO MY ACCOUNT VIEW AND MANAGE MY TASKS | REGISTERED USER | LOG INTO MY ACCOUNT | VIEW AND MANAGE MY TASKS | 4 | JASON | 1
1.3 | REGISTERED USER BE NOTIFIED IF MY LOGIN ATTEMPT FAILS TROUBLESHOOT OR RETRY | REGISTERED USER | BE NOTIFIED IF MY LOGIN ATTEMPT FAILS | TROUBLESHOOT OR RETRY | 2 | SARAH | 1
1.4 | REGISTERED USER BE REDIRECTED TO A SUCCESS PAGE UPON SUCCESSFUL LOGIN KNOW I HAVE LOGGED IN SUCCESSFULLY | REGISTERED USER | BE REDIRECTED TO A SUCCESS PAGE UPON SUCCESSFUL LOGIN | KNOW I HAVE LOGGED IN SUCCESSFULLY | 2 | SARAH | 1

## Class UML
User
- name: String
- email: String
- Password: String
+ Register()
+ Login()
Table: Users
| ID | Name | Email | Password
| 1 | John Smith | john@example.com | *******
| 2 | Sarah Schneider | sarah@example.com | *******
| 3 | Mark Smithers | mark@example.com | *******
TITLE SCREEN
REGISTRATION PAGE
LOGIN FAILURE PAGE
LOGIN SUCCESS PAGE

## Burn Down Chart
BURNDOWN CHART
DATE | PLANNED EFFORT | ACTUAL EFFORT
19-JUN | 10 | 10
20-JUN | 8 | 7.5
21-JUN | 6 | 6.5
22-JUN | 4 | 4
23-JUN | 2 | 2.5
26-JUL | 0 | 0